## Project Plan
| Procurement Act 2023 - Project Tracking Document | [8 empty] | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01 |  |  |  |  | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  | 2024-07-01 |  |  |  |  | 2024-08-01 |  |  |  | 2024-09-01 |  |  |  | 2024-10-01 |  |  |  | 2024-11-01 | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  | 2025-03-01
 | time axis 2024-01-01 to 2025-03-31
No | AT RISK | STATUS | PRIORITY | START DATE | DEADLINE | TASK | DESCRIPTION | Allocated tasks within activity | ASSIGNED TO
|  |  | as at Jan xx |  |  | Knowledge Sharing / Awareness
1 |  | In Progress | High |  | 2024-02-19 | Procurement Team Training Planner | Planner to tracked training schedule with BLC for Procurement Team. Track super user TPP completion and Super User deep drive bookings. | Complete and tracking completion of the E-learning to ensure all complete by Oct 2024. | bar: 2024-01-08
2 |  | Not Started | High |  | 2024-02-29 | New starter Old regs knowledge | Assess old regs knowledge for new starters and address gaps prior to PA2023 training. | To review on a case by case basis. | bar: 2024-01-08 to 2024-02-26
3 |  | Not Started | Medium | 2024-04-15 |  | Wider stakeholder Awareness Training planner | Plan to knowledge share changes in the reglations with wider stakeholders. | bar: 2024-04-15
4 |  | Not Started | Medium |  | 2024-05-31 | Communication to suppliers | Initial communicate with those outside central digital platform inc SME's. | bar: 2024-05-06 to 2024-06-03
5 |  | Not Started | High |  | 2024-03-18 | Knowledge drops / Fact sheets for Procurement Team | GCF material to share at Standups | bar: 2024-01-08 to 2024-03-18
6 |  | Not Started | Medium |  | 2025-02-01 | Superuser nomination and events | Plan events and communication channels to ensure use and uptake of superusers | bar: 2024-01-08 to 2024-03-18
7 |  | Not Started | High |  | 2024-04-01 | Training sign up | Manage team to ensure training booked for the allocated time window and monitor successful completion. | bar: 2024-02-05 to 2024-03-25
8 |  | Not Started | Low | 2024-11-01 | Ongoing | In2 training | Consider In2 training as part of training schedule | bar: 2024-10-28 to 2025-02-24
9 |  | Not Started | Low | 2024-04-01 | Ongoing | Knowledge drops | Watch and share with key stakeholders as part of training schedule implementation plan. | bar: 2024-10-28 to 2025-02-24
10 |  | Not Started | Low | 2024-04-01 | 2024-12-01 | E-learning | Ensure right stakeholders are enrolled and complete e-learning training and obtain certification | bar: 2024-04-01 to 2024-12-30
11 |  | Not Started | Low | 2024-09-01 | 2025-01-01 | Advanced course deep dives | 3-day instructor led course for super users | bar: 2024-10-07 to 2025-02-03
12 |  | Not Started | Medium | 2024-08-01 | 2025-02-01 | Upskilling others - internal training and support | Prepapre guidance documents, communications, super users, champions to embed the new ways of working across the organisation - including transitional arrangements | bar: 2024-08-05 to 2025-02-24
13 |  | Not Started | Medium | 2025-01-01 | 2025-03-01 | Embed process - operational | Carry out training workshops on new processes with key stakeholders at operational level | bar: 2025-01-13 to 2025-03-31
14 |  | Not Started | Medium |  | 2024-09-01 | SME support | How do we educate and support - community event / roadshow Target certain commodity suppliers? | bar: 2024-09-02
15 |  | Not Started | Medium |  | 2024-04-01 | Identify peers and other public sector organisations | Identify contacts as good point for infor sharing discussions. | bar: 2024-02-05 to 2024-04-15
Procurement Activities
16 |  | In Progress | High |  | 2024-11-01 | Implementation plan | Create implementation and submit for approval | bar: 2024-10-28
17 |  | Not Started | Medium |  | 2024-11-01 | Risk Register | Identify and manage risks to implementation | bar: 2024-10-28
18 |  | Not Started | High |  | 2024-04-01 | Recruitment of additional resource | Recruit to deliver (Agency) or internal support and backfill? | bar: 2024-04-01 to 2024-04-29
19 |  | Not Started | High |  | 2024-05-31 | Update contact info on IT systems | Ensure supplier contact info correct (not invoicing) and check re: sending out comms through this system v others like EU supply/Intend. | bar: 2024-06-03
20 |  | In Progress | High |  | 2024-10-01 | Procurement pipeline | Review procurement pipeline to identify high risk procurements under the new Act to inform resource planning | bar: 2024-09-30 to 2024-10-21
21 |  | Not Started | High |  | 2025-02-01 | Procurement Approach | Review the current ways of approaching procurements and assess what doesn't align to new regs. Ie - choose framework as Direct award available. | bar: 2024-09-30 to 2025-01-27
22 |  | Not Started | High |  | 2025-02-01 | Procurement process update | Conduct analysis to identify where procurement process needs to be updated | bar: 2024-09-30 to 2025-01-27
23 |  | Not Started | High |  | 2025-02-01 | Procurement process design | Conduct analysis to identify where new process must be designed and implemented | bar: 2024-09-30 to 2025-01-27
24 |  | Not Started | High |  | 2025-02-01 | Procurement procedures | Update templates for each procurement procedure to reflect PA 2023 requirements and new process | bar: 2024-09-30 to 2025-01-27
25 |  | Not Started | High |  | 2025-02-01 | Procurement guidance | Update of procurement guidance to reflect new and updated procurement process | bar: 2024-09-30 to 2025-01-27
26 |  | Not Started | High |  | 2025-02-01 | Mulitple legislation | Consider how the use of two regimes will be reflected in guidance and process | bar: 2024-09-30 to 2025-01-27
27 |  | Not Started | High |  | 2025-02-01 | Contract Register | Ensure contract register is up to date and captures information of which reigme the contract was procured under | bar: 2024-09-30 to 2025-01-27
28 |  | Not Started | Medium |  | 2025-02-01 | Market engagement | Review market engaement process and how to be utilised in new regime. Consider level of engagement for low, medium or high value/risk procurements, and appropriate criteria | bar: 2024-09-30 to 2025-01-27
29 |  | Not Started | High |  | 2025-02-01 | Procurement notices | Map out notice requirements for each procurement procedure and ensure these are reflected in procurement policy and process | bar: 2024-09-30 to 2025-01-27
30 |  | Not Started | Medium |  | 2025-02-01 | Exemption Trackers | Review and analyse the reasons and assess what the risk is around breaches of the new regulations. | bar: 2024-09-30 to 2025-01-27
31 |  | Not Started | High |  | 2024-03-31 | Assess regularly used frameworks | What are the validity of the frameworks. Assess those expiring up to April 25 - are they likely to be extended or re-competed under new regs. Any issues identified that could force local tender? | bar: 2024-04-01
32 |  | Not Started | High |  | 29/02/2023 | Workplan updates | 1. Look at capacity to undertake training. 2. Review contracts expiring pre Feb25 (old regs) v Post (new regs) 3. Reasonable reprocurement timelines to deliver esp. new regs? 4. Identify those tenders going first | bar: 2024-03-25
33 |  | Not Started | High | 2024-06-01 | 2024-09-09 | Admin updates | 1. Toolkit refresh 2. Principles of PA 2023 captured in document set - ie SME friendly docs and instruction eg below threshold? | bar: 2024-12-30 to 2025-01-27
Corporate
34 |  | In Progress | High | 2024-03-13 | 2024-12-01 | Procurement strategy | Consider PCC's objectives and policy, including green agenda, SME's, buying local and ensure alignment with new procurement strategy | bar: 2024-09-02 to 2025-01-06
35 |  | Complete | High | 2024-03-13 | 2024-09-02 | Update Standing orders and Contract regulations | Engage IN2 the bargain to update | bar: 2024-03-04 to 2024-09-23
36 |  | Not Started | Medium |  | 2024-09-02 | Standing orders on a page | To reflect re-draft when agreed | bar: 2024-09-30 to 2024-11-25
37 |  | Not Started | Medium |  | 2024-09-20 | Procurement Hub | Ensure information current, review content / engaging# GCF videos Timelines and rules standing orders | bar: 2024-09-30 to 2024-11-25
38 |  | Not Started | Medium | 2024-04-15 |  | Communications Plan | Communication plan - use to promote PA 2023 and commercial - ensure Proc Hub clear in content to support comms work. | bar: 2024-04-01 to 2024-05-06
Digital
39 |  | Not Started | Medium |  | 2025-02-01 | Website and intranet update | Update the website and intranet with new policy and process once approved through governance | bar: 2024-10-28 to 2025-02-24
40 |  | Not Started | High |  | 2025-02-01 | Intend update | Communicate with Intend and understand updates to the procurement system to be compliant with PA 2023, including new notices and how Intend will interface with the central digitial platform | bar: 2024-10-28 to 2025-02-24
41 |  | Not Started | Medium |  | 2025-02-01 | Central Digital Platform | Investigate and reflect the Central Digitial Platform in required policy and process | bar: 2024-10-28 to 2025-02-24
42 |  | Not Started | High |  | 2025-02-01 | Data collection requirements | Understand data collection requirements for new legislative requirements, including conflicts of interest, debarment, due diligence, financial reporting, performance reporting and contract changes. | bar: 2024-10-28 to 2025-02-24
43 |  | Not Started | High |  | 2025-02-01 | Data collection process | Conduct gap analysis to understand if this data can be collected by current systems or processes, or if further changes to systems and process is required. | bar: 2024-10-28 to 2025-02-24
44 |  | Not Started | High |  | 2025-02-01 | Roles and responsibilities | Map out roles and responsibilities for data collection and reporting between stakeholders to ensure clarity over who is repsonsible for complying with each pocess | bar: 2024-10-28 to 2025-02-24
Assurance
45 |  | Not Started | Medium | 2024-06-01 | 2024-10-01 | Check understanding | How do we check team understanding after training? Gaps in knowledge to be identified - old and new regs. | bar: 2024-09-30
46 |  | Not Started | Low |  | 2025-09-01 | Internal audit | Request internal audit to conduct a review to ensure procurement processes are compliant and be carried out in line with new policy and procedures. | bar: 2025-03-31
47 |  | Not Started | Medium |  | 2025-02-01 | Conflict of interest | Design new conflict of interest process to ensure compliance with new regulations | bar: 2025-03-31
48 |  | Not Started | Medium |  | 2025-07-01 | Walkthroughs | Conduct walkthroughs of procurements undertaken on the new Act to ensure compliance and identify lessons learned | bar: 2025-03-31
49 |  | Not Started | Low |  | 2025-09-01 | Lessons learned | Collect lessons learned and feedback on the new procurement processes and systems | bar: 2025-03-31
Contract Management
51 |  | Not Started | High |  | 2024-12-01 | Gap analysis | Conduct a gap analysis to understand the understanding of contract managers of the new requirements under PA 2023, and the role of contract management in the new procurement processes. | bar: 2024-10-28 to 2024-12-30
52 |  | Not Started | Medium |  | 2024-12-01 | Roles and responsibilities | Review and assign roles and responsibilities that are relevant to contract management as part of the new PA 2023 legislative requirements and processes | bar: 2024-10-28 to 2024-12-30
54 |  | Not Started | Medium |  | 2025-02-01 | Training | Conduct appropriate training of contract managers to understand their roles and responsibilities and ensure information is being collected and notices published as required under new process | bar: 2024-12-09 to 2025-03-03
54 |  | Not Started | High |  | 2025-02-01 | Contract management process | Update and design new process to ensure contract management processes are compliant with PA 2023 | bar: 2024-12-09 to 2025-03-03
55 |  | Not Started | High

## Training schedule
Procurement Act Training Planner
Organisation Name: Staffordshire Police
Name | email address | Job role | Superuser | Training Priority | 10 Hours e-learning | 3 days tutor led deep dive training | 10th Sept 2024 | 17th Sept 2024 | 30th Sept 2024
|  | Head of Commercial Services | Y/N | 1 | 2024-04-01 | June-August 24 | Super User Complete
|  | CBP | Y | 1 | 2024-04-01 | June-August 24 | Super User Complete
|  | CBP | Y | 2 | 2024-04-01 | June-August 24 | Super User Complete
|  | CBP | Y | 3 | 2024-04-01 | June-August 24 | Super User Complete
|  | Procurement Officer | N | 4 | May-June 24 | Sept-Oct 24 |  | 8 | 8
|  | Procurement Officer | N | 5 | May-June 24 | End of Nov 24 | Super User Booked
|  | Procurement Officer | N | 6 | Sept-Oct 24 | June-August 24 |  | 6 | 6
|  | Procurement Officer | N | 7 | May-June 24 | June-August 24 |  | 4 | 6
|  | Procurement Officer | N | 8 | May-June 24 | Nov - Dec 24 |  | 8 | 9
|  | Procurement Officer | N | 9 | Sept-Oct 24 | Jan - Feb 25 |  | tbc | 4
|  | Agency |  | 11 | Sept- Oct 24 | n/a | Deep Dive Complete

## Key
Key
STATUS KEY | PRIORITY KEY
Not Started | High
In Progress | Medium
Complete | Low
On Hold
Overdue